## Backlog
Issue type (bug, task, etc) | Issue | Estimated Effort | Task Owner | Completed?
Task | (SRS) Adding an editing option (similar to delete) for all accounts within the Admin Page. The Admin could edit the name of an account, the email, phone number, … and whatever other info is appropriate. It’s up to R&D if this should be a pop-up display box with the editable info, if the info is automatically editable in the line of info after double-clicking edit, or if they want it to be a separate page. | Small | Kendahl & Alex | TRUE
Task | (SRS) Adding in functionality to open up a specific contribution/upload through clicking on a button labeled “view more” at the bottom of the descriptive box which will open up a new page that lists that contribution along with all other contributions within that same area/on that same pin. Refer to SRS | Small | Gavin & Michael | TRUE
Task | (SRS) Adding functionality to the requirement “2.1.4.8 Admin Add a Filter”. The process is currently unknown and only the button will exist on the webpage. Ask R&D how it is set up in the database (info necessary to add a filter) and in general, what this process is. | Small | John & Daniel & Malik | TRUE
Task | FLIER WITH QR CODE, QR code created, flier in progress, waiting on client response | Small | Kendahl & Alex | TRUE
Task | (STP) All tests were written in relation to the SRS but none have been tested. Reach out if any questions/comments/concerns arise. https://docs.google.com/spreadsheets/d/1cq4kdxZPHimY4N7v7Nw8LWtl3aS_fAO2/edit?usp=sharing&ouid=109500913347840036355&rtpof=true&sd=true | Small | Gavin & Michael | FALSE
Task | Porting Azure HTML to Django | Medium | Alex S | TRUE
Task | Getting everyone on GIT | Small | Sam | TRUE
Task | Make main branch Django branch | Small | Sam | TRUE
Task | Work on new database Schema | Large | Dexter and Alex S | TRUE
Task | Fix google maps API issues | Small | Alex | TRUE
- | Updating and cleaning up About Us Page | Medium | Nathan | TRUE
Task | Updating and cleaning Map Create a Post | Small | Roman | FALSE
Task | Contact us form needs to be updated | Medium | Jeffrey and Roman | TRUE
Task | Tracablility Matrix | Large | John and Malik | TRUE
Task | Read Github files (ending in .html, .css, .json mostly), if you cannot understanding what is going on in the code, flag it for comments. otherwise, leave alone. Do not comment yourself. To be Documented within the shared drive. Please specify 1.) FILE PATHWAY 2.) LINE to where comment should be added & 3.) Description or reason for flagging i.e "needs comment" or "elaborate" | Small | Gavin, Michael, Alex O, and Kendalh. | TRUE
Task | Package Deployment | Medium | Sam | TRUE
Task | Overall HTML overhaul | Small | Alex S | TRUE
Test | Testing About Us and Contact Us pages (fill out contact us form) Should rei | Small | John and Malik | FALSE
Task | Sign In page UI overhaul | Medium | Nathan | TRUE
Task | Google map page UI overhaul | Medium | Nathan | TRUE
Task | Look into pivot table to keep track of testing | Small | Gavin and Michael | TRUE
Task | Standardizing Site and Fonts | Small | Roman | TRUE
Task | Standardize STP Codes | Small | John and Malik | TRUE
Task | Updating FAQ page CSS and Stacks | Small | Nathan | TRUE
Task | Updating Account Page | Small | Jeffery | FALSE
Task | Re-Organize the CSS | Medium | Roman | FALSE
Task | Formatting My account page | Small | Nathan | TRUE
Task | Formatting account sidebar | Small | Quinnten | TRUE
Task | Formatting Map page | Medium | Roman | TRUE
Task | Django doc for fall r&d | Medium | Daniel and John | FALSE
Task | Work on .css for Pending Post view for admin | Medium | Quinnten | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## R&D Site Functionality Backlog
Issue type (bug, task, etc) | Issue | Priority | Estimated Effort | Task Owner | Completed?
Task | Create view: all accounts, link to specific user account view | High | Medium |  | TRUE
Task | Create view: specific account, show all user's visible posts, profile picture, email, aboutme, etc | High | Medium |  | TRUE
Task | Update post model: allow for user uploaded media | High | Large | Alex S | TRUE
Task | Update view: specific post, report button, show location on js map, slideshow container with google map and user uploaded media | High | Large | Alex S | TRUE
Task | Create views for admin managing of posts | High | Medium | Dexter | TRUE
Task | Create views for admin managing of users | High | Medium | Dexter | TRUE
Task | Update user model: banned rank, update all views to restrict banned user to viewing and nothing else | Low | Medium | Dexter | FALSE
Task | Update post model: change isVisible boolean to choices -1,0,1, corresponding to denied, pending, visible. when denied, set post.description to rejection reason | Medium | Small | Dexter | TRUE
Task | Create custom google map ID https://developers.google.com/maps/documentation/javascript/advanced-markers/start | High | Small | Dexter | TRUE
Task | Create view: my posts, separate into pending, denied, visible | Medium | Medium |  | FALSE
Task | When account first made, make user complete profile before attempting to post | Low | Medium |  | FALSE
Task | Create view: allow exporting of data | Low | Large |  | FALSE
Task | Create view: make post, available under contributor tab to signed in users. | Low | Medium | Dexter | TRUE
Task | let admin set contact requests as read | Low | Small |  | FALSE
Task | create user/pass login schema | Medium | Large |  | FALSE
Task | create what it means to be contributor page, set to default account page |  | Small |  | FALSE
Task | create a make account page |  | Medium |  | FALSE
Task | create a new sign in page, separate from the default |  | Small |  | FALSE
Task | fix the my account template |  | Small |  | FALSE
Task | add report form to individual account page |  | Medium |  | TRUE
Task | create account sort/search |  | Medium |  | FALSE
Task | Clean up slideshow view |  | Small |  | FALSE
Task | add navlinks visible only to admin on an account/post view that link to the admin manage view for that post/account |  | Small |  | FALSE
|  |  | Small |  | FALSE
|  |  | Small |  | FALSE
|  |  | Small |  | FALSE
|  |  | Medium |  | FALSE
|  |  | Small |  | FALSE
|  |  | Small |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE