## R&D
Issue type (bug, task, etc) | Issue | Estimated Effort | Task Owner | Completed?
Task | Django training 9/23/24 - 10/2/24 Objectives | Large | Everyone | TRUE
Task | Python training 9/23/24 - 10/2/24 Objectives | Small | Everyone | TRUE
Task | GIT Training 9/23/24 - 10/2/24 Objectives | Medium | Everyone | TRUE
Task | Getting everyone on GIT | Small | Leah | TRUE
Task | get everyone up to date with the project progress (folks who were here last semester can contribute) | Small | Roman | TRUE
Task | Rework CCC Forums | Large |  | FALSE
Task | Fix CCC Accounts | Medium | Roman | TRUE
Task | Rework CCC Forums (Forum page remodel) | Medium | Nathan & Mia | FALSE
Task | Rework CCC Forums (Post page creation) | Medium | Nathan & Mia | FALSE
Task | Rework CCC Forums (Forum page pagination (for Posts) |  | Quinten & Anthony | FALSE
Task | Rework CCC Forums (Post page pagination (for Comments)) |  | Quinten & Anthony | FALSE
Task | Load Django Using Apache | Large | Jeffrey | FALSE
Task | Port CCC to PostgreSQL | Medium |  | FALSE
Task | Begin Using Google Cloud | Medium | Alex Ochman | FALSE
Task | Find the Database Password | Medium | CD Spec Team | FALSE
Task | Add Sustainable Development Goals Tags (With Icons) | Small |  | FALSE
Task | Admin Page (Admins can promote others to Admins and Mods) | Medium |  | FALSE
Task | Admin Page (Mods can promote others to Mods) | Medium |  | FALSE
Task | Admin Page (Admins and Mods can add and remove Contributors from a Forum) | Medium |  | FALSE
Task | Load CCC and CD Spec into Google Cloud | Medium | Roman | TRUE
Task | Create a MySQL or MarinaDB database. One data base instance, two database accounts. | Small | Roman | TRUE
Task | Extract CD Spec's PostreSQL database into MySQL or MarinaDB. |  |  | FALSE
Task | Return from Django password verification what is wrong with the password (account/signup.html) | Small | Kayla | FALSE
Task | (Account) Render Forums, Posts, and Comments under a User's account. | Large | Kayla & Kendahl | TRUE
Task | (Account) Make the rendered Forums, Posts, and Comments look pretty on the User's account. | Medium | Kendahl | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## QA
Issue type (bug, task, etc) | Issue | Estimated Effort | Task Owner | Completed?
Task | Django training | Large | Everyone | TRUE
Task | Python training | Small | Everyone | TRUE
Task | GIT Training | Medium | Everyone | TRUE
Task | Write automated tests for CDSpec with Django | Large | Philip | FALSE
Task | ADA Compliance report (read docs and figure out issues with CCC site) | Medium | Oliver | TRUE
Task | Finding solutions for authorization | Large | Gus, Jacob, Sam | TRUE
Task | Familiarize with Django Automatic testing | Medium | Everyone | TRUE
Task | Read Docs and Figure out what tests need to be done to comply with client requirements | Medium | Everyone | TRUE
Task | Write automated tests for CCC with Django | Large | Philip | FALSE
Task | comment legacy code | Large | Kester, Ben, Andrew, Abdoul | FALSE
Task | Update STP Doc | Small | Michael | FALSE
Task | Add Google Cloud API sign in to CDSpec | Large | Gus | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE